## Cover
Product Discovery & Decision Log
Merchant Payment Operations & Dispute Hub
Version | 2.0
Date | 2026-09-11
Prepared by | Bhawna, Product Owner
Purpose | Records what market and internal discovery showed, the gap it revealed, and the product decision taken or proposed, with sources and links to the roadmap, KPIs and wireframes.
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client system. External sources were accessed on 11 September 2026; vendor blogs may be promotional.
Summary
Decision status | Count | Horizon | Count
Approved | 6 | MVP | 8
Approved with conditions | 1 | Next | 4
Pending decision | 1 | Later | 3
Proposed | 7
Needs evidence | 0
Total decisions | 15
Status values
Approved | Decided and in the plan.
Approved with conditions | Decided, with conditions that must be met (see Next step).
Pending decision | Waiting on a named decision, usually a change request.
Proposed | Recommended by discovery but not yet approved or funded.
Needs evidence | Hypothesis without enough evidence to decide.

## Discovery & Decisions
Discovery & Decisions
Merchant Payment Operations & Dispute Hub · Simulation project · Evidence cites the Sources tab
ID | Theme | What we discovered | Evidence | Sources | Gap or implication | Product decision | Decision status | Decision owner | Decision date or due | Horizon | Linked items | Next step
DSC-01 | Workflow | Disputes need one action-oriented workspace | Amex's online Disputes tool shows all inquiries and chargebacks at once, with those needing a response first. Adyen's Customer Area lists disputes with days left to defend and the latest event. Razorpay lets merchants view, accept and contest disputes from one dashboard. | SRC-01, SRC-07, SRC-11 | Email and spreadsheets split ownership and hide what needs action. | Build a single Merchant Dispute Hub inbox and dispute detail | Approved | Business Sponsor | 2026-07-17 | MVP | EP-02, US-006, US-009, BR-01, S01, S02 | Delivered in Sprints 2–3; validate in pilot
DSC-02 | Workflow | Deadline visibility decides outcomes | Adyen shows days left to defend in its dispute list. Amex requires a response by the reply-by date, or a chargeback is issued. | SRC-02, SRC-07 | A status alone doesn't tell merchants what is due and when. | Deadline-first inbox, countdown highlighting and reminders at 5 and 2 days | Approved | Business Sponsor | 2026-07-17 | MVP | US-011, US-025, KPI-03, KPI-04, S01, S02 | US-011 in progress; US-025 in Sprint 6
DSC-03 | Evidence | Evidence submission should be guided | Amex shows a list of acceptable supporting documents for most cases. Razorpay asks merchants to pick an evidence type for each document. | SRC-06, SRC-11 | Generic file upload produces incomplete evidence. | Reason-code evidence checklist, file validation and plain-language reasons | Approved | Product Owner | 2026-08-27 | MVP | US-007, US-012, CR-02, BR-03, BR-21, S02, S03 | Design sign-off pending (I-03)
DSC-04 | Trust and data | Status alone doesn't create trust | Adyen and Razorpay send webhook or email updates when dispute status changes. | SRC-07, SRC-12 | Merchants, Ops and Finance can read statuses differently, and stale data causes missed deadlines. | Canonical status model, last-synced timestamp, feed-freshness alerts and reconciliation | Approved | Tech Lead | 2026-08-27 | MVP | US-010, US-020, US-023, DEF-03, KPI-12, KPI-13 | Fix DEF-03 mapping defect in Sprint 4
DSC-05 | Workflow | Email should notify, not carry the workflow | Amex moves disputes out of letters into one online place with email notifications. Razorpay sends email notifications and takes responses through its dashboard and API. | SRC-01, SRC-03, SRC-12 | Email-led handling keeps Ops cost high and evidence uncontrolled. | Portal is the system of action; email only notifies; retire email intake wave by wave | Approved | Dispute Ops Lead | 2026-09-10 | MVP | IR-12, RM-19, KPI-05, KPI-06 | Retirement steps in Post-Launch Plan (BAU Transition)
DSC-06 | Market | A disputes portal is table stakes, including at Amex | Amex already offers online dispute responses, document upload (up to 20 pages and 5 files per case), email notifications and downloadable reports. | SRC-01, SRC-03, SRC-04 | A portal alone won't differentiate, especially for an Amex audience. | Position the hub as network-agnostic, with prevention and explainable AI on top of the core portal; use Amex terms (Card Member, inquiry, reply-by date) | Approved | Product Owner | 2026-09-11 | MVP | Executive Review deck, PRD section 16.4 | Reflect in interview narrative and executive deck
DSC-07 | AI | Evidence preparation is being automated | Stripe Smart Disputes builds evidence packets and submits them automatically before the deadline if the merchant doesn't act. Visa's representment tool uses generative AI and win-prediction scoring. | SRC-08, SRC-13 | Manual evidence gathering is slow and often incomplete. | AI evidence copilot drafting packets from connected source systems | Proposed | Steering Committee | 2027-05-27 | Next | RM-26, KPI-20, S10 | Discovery and business case before the Phase 2 funding decision (MS-09)
DSC-08 | AI | AI in disputes needs data and human guardrails | Stripe states merchants remain responsible for the accuracy of packet data. Much winning evidence sits in carriers, CRMs and helpdesks rather than the payment platform. | SRC-08, SRC-18 | Unverified AI-generated content creates accuracy, compliance and trust risk. | AI uses only real source records, shows every source, and requires human review above a set amount | Proposed | Compliance Lead | 2027-06-17 | Next | RM-26, S10, MS-11 | AI copilot model risk review (MS-11)
DSC-09 | Prevention | The best intervention happens before a chargeback | Amex Accelerated Dispute Resolution sends a Dispute Alert with up to 8 calendar days to respond before normal disputes processing (US merchant IDs, non-fraud). Stripe resolution rules can refund eligible disputes automatically. | SRC-05, SRC-09, SRC-10 | Fighting every dispute after it becomes a chargeback is costly and reactive. | Pre-dispute alerts with early refund and order-detail recommendations | Proposed | Dispute Ops Lead | 2027-05-27 | Next | RM-25, KPI-19, S09 | Confirm alert programs and per-alert costs with the acquirer
DSC-10 | Prevention | Dispute ratio is a business-health signal | Card networks penalize merchants whose dispute ratios cross monitoring thresholds. One in five merchants say Visa's VAMP changes affected them, and only 26.8% monitor TC40 fraud records. Amex runs its own chargeback and fraud monitoring programs. | SRC-15, SRC-17, SRC-20 | Merchants discover threshold risk too late. | Dispute ratio health view with alerts at 60% and 80% of thresholds | Proposed | Merchant Relationship Lead | 2027-03-11 | Next | RM-28, KPI-21, S11 | Confirm ratio data source and current thresholds with the acquirer
DSC-11 | Prevention | Dispute data can reveal root causes | Alert data shows which products, price points and traffic sources generate disputes fastest, and belongs in screening decisions rather than static reports. | SRC-19 | Reporting what happened doesn't prevent it happening again. | Root-cause insights by product, billing name and channel, with recommended fixes | Proposed | Product Owner | 2027-11-30 | Later | RM-29, S12 | Revisit at 2028 roadmap planning (MS-13)
DSC-12 | Trust and data | Finance and Ops need one outcome definition | Finance and Ops calculate win rate differently on the same disputes (40% vs 62.5% in the worked example). | SRC-21 | Leadership receives numbers the teams don't agree on. | Report Won, Partially won and Lost separately, with value recovery as the North Star (CR-05 Option C) | Pending decision | Business Sponsor | 2026-09-18 | MVP | CR-05, I-05, KPI-01, KPI-02, US-032 | Decision meeting 17 Sep; update KPI definitions after
DSC-13 | Security | Security is part of the product | Card numbers appear in emailed evidence today, expanding PCI DSS exposure. | SRC-21 | Email attachments create uncontrolled evidence handling. | Secure upload with card-number redaction, quarantine and InfoSec validation | Approved with conditions | Steering Committee | 2026-09-04 | MVP | CR-03, R-02, US-013, US-014, BR-04, CTL-01 | InfoSec validation before UAT sign-off (LR-03)
DSC-14 | Prevention | Friendly fraud can now be fought with transaction history | Visa Compelling Evidence 3.0 and Mastercard First-Party Trust let merchants overturn fraud claims with earlier undisputed purchases sharing identifiers. Visa enabled CE 3.0 inside Order Insight from 1 April 2026. 83.4% of enterprise merchants saw friendly fraud rise over three years. | SRC-13, SRC-14, SRC-15 | Merchants lose disputes they could win because the matching history isn't assembled. | Automate friendly fraud evidence matching inside the AI copilot | Proposed | Product Owner | 2027-11-30 | Later | RM-27, S10 | Confirm network eligibility rules; Amex follows its own process
DSC-15 | Market | AI shopping agents change what evidence exists | When an AI agent buys, the usual click and device trail largely disappears. Visa agent tokens and Mastercard Agent Pay aim to create agent-specific records but are still maturing. Monitoring thresholds don't change for agent purchases. | SRC-16, SRC-17 | Merchants may be unable to defend agent purchases, and ratios can spike. | Capture agent authorization records and track agent-initiated disputes as their own channel | Proposed | Tech Lead | 2027-11-30 | Later | RM-30, S13, S11 | Track standards; revisit at 2028 roadmap planning (MS-13)

## Sources
Sources
All external sources accessed 11 September 2026. Check vendor blogs against official documentation before relying on them.
ID | Publisher | Title | URL | Source type | Published | Used by
SRC-01 | American Express | Disputes Support Center for Merchants (US) | https://www.americanexpress.com/us/merchant/support-center/disputes.html | Official product help | Not stated | DSC-01, DSC-05, DSC-06
SRC-02 | American Express | Managing a Dispute Case | https://www.americanexpress.com/us/merchant/support-center/disputes/managing-a-disputes-case.html | Official product help | Not stated | DSC-02
SRC-03 | American Express | Why Manage Disputes Online (US) | https://www.americanexpress.com/us/merchant/support-center/disputes/why-manage-disputes-online.html | Official product help | Not stated | DSC-05, DSC-06
SRC-04 | American Express | Adding Documents to a Case | https://www.americanexpress.com/us/merchant/support-center/disputes/adding-documents-to-a-case.html | Official product help | Not stated | DSC-06
SRC-05 | American Express | Logging In and Enrolling in Disputes (Accelerated Dispute Resolution) | https://www.americanexpress.com/us/merchant/support-center/disputes/logging-in-and-enrolling.html | Official product help | Not stated | DSC-09
SRC-06 | American Express | Merchant Website Support Centre (accepted supporting documents) | https://www.americanexpress.com/ac/merchant/support-centre.html | Official product help | Not stated | DSC-03
SRC-07 | Adyen | How can I get chargeback/disputes notifications and updates? | https://help.adyen.com/en_US/knowledge/risk/dispute-management/how-can-i-get-chargeback-disputes-webhooks-and-updates | Official product help | Not stated | DSC-01, DSC-02, DSC-04
SRC-08 | Stripe | Smart Disputes (documentation) | https://docs.stripe.com/disputes/smart-disputes | Official product docs | Not stated | DSC-07, DSC-08
SRC-09 | Stripe | Dispute prevention (documentation) | https://docs.stripe.com/disputes/prevention-preview | Official product docs | Not stated | DSC-09, DSC-14
SRC-10 | Stripe | Introduction to payment disputes (guide) | https://stripe.com/guides/introduction-to-payment-disputes | Official guide | Not stated | DSC-09
SRC-11 | Razorpay | Disputes: Dashboard Actions | https://razorpay.com/docs/payments/disputes/dashboard/?preferred-country=US | Official product docs | Not stated | DSC-01, DSC-03
SRC-12 | Razorpay | About Disputes | https://razorpay.com/docs/payments/disputes/ | Official product docs | Not stated | DSC-04, DSC-05
SRC-13 | Digital Commerce 360 | Visa adds AI tools for dispute resolution | https://www.digitalcommerce360.com/2026/04/01/visa-adds-ai-tools-for-dispute-resolution/ | Industry news | 2026-04-01 | DSC-07, DSC-14
SRC-14 | The Paypers | Chargebacks: issuer fraud verdicts and the impact of agentic commerce | https://thepaypers.com/fraud-and-fincrime/expert-views/chargebacks-issuer-fraud-verdicts-and-the-impact-of-agentic-commerce | Industry expert view | Not stated | DSC-14
SRC-15 | Chargebacks911 | 2026 Chargeback Field Report | https://chargebacks911.com/chargeback-field-report/ | Vendor research | 2026-06-30 | DSC-10, DSC-14
SRC-16 | Justt | Agentic Commerce Chargebacks and the Evidence Gap | https://justt.ai/blog/solving-agentic-commerce-chargebacks/ | Vendor blog | 2026-07-02 | DSC-15
SRC-17 | Chargeflow | AI Agent Chargeback Liability | https://www.chargeflow.io/blog/ai-agent-chargeback-liability | Vendor blog | 2026-07-28 | DSC-10, DSC-15
SRC-18 | Chargeflow | What Stripe Smart Disputes covers and what it doesn't | https://www.chargeflow.io/blog/what-stripe-smart-disputes-covers-and-what-it-doesnt | Vendor blog (competitor of Stripe) | 2026-07-19 | DSC-08
SRC-19 | Wyllo | Chargeback Prevention in Ecommerce: 2026 Guide | https://wyllo.ai/chargeback-prevention-ecommerce-2026/ | Vendor blog | 2026-07-17 | DSC-11
SRC-20 | chargeback.io | How to Win an American Express Dispute | https://www.chargeback.io/blog/how-to-win-an-american-express-dispute | Vendor blog | 2026-08-03 | DSC-10
SRC-21 | Internal | RAID Log and Change Log (simulation project) |  | Internal project record | 2026-09-10 | DSC-12, DSC-13

## Change Notes
Change Notes: version 1 to version 2
Type | Change | Why
Structure | Renamed Sheet1 and added Cover, Sources and this Change Notes tab. | Makes the log shareable and auditable.
Structure | Added IDs (DSC-), themes, decision status, owner, date, horizon, linked items and next step to every row. | A decision log needs to show who decided what, when, and what it affects.
Sources | Every evidence statement now cites a source ID with URL, type and published date where known. | Claims can be checked; vendor blogs are labelled as such.
Status | Outcome framework marked Pending decision (CR-05). AI copilot, pre-dispute alerts, ratio health, root-cause insights, friendly fraud automation and agent readiness marked Proposed. | They weren't approved anywhere; the original log presented them as decided.
Added | DSC-06 (Amex already offers online disputes), DSC-14 (friendly fraud evidence rules) and DSC-15 (AI shopping agents). Amex ADR and Razorpay evidence added to existing rows. | Covers the most relevant market evidence for an Amex audience.
Removed | Claim that Adyen moved UPI dispute handling into its Customer Area, and the Mastercard end-to-end dispute management positioning. | No source could be found; re-add only with a verifiable source.
Linked | Decisions now link to roadmap initiatives RM-25 to RM-30, KPI-19 to KPI-21 and wireframes S01 to S13. | Keeps the log consistent with the roadmap, PRD, KPI catalog and wireframes.