## Cover
Engagement Plan
Merchant Payment Operations & Dispute Hub
Document | Engagement overview, stakeholder engagement, RACI, governance, communications and deliverables
Version | 1.0
Reporting date | 2026-09-10
Prepared by | Bhawna, Product Owner
Companion documents | RAID_Log, Change_Log, Product_Backlog, RTM, KPI_Definitions and Business_Case_GTM workbooks
Project type | Simulation / portfolio project prepared to demonstrate Product Owner practice. Not an actual client engagement; stakeholders are roles, not real people, and all dates are illustrative.
Purpose
Sets out how the engagement is run and how stakeholders are brought along: what we are delivering and why, who needs to be involved and how, who decides what, which forums make decisions, how we communicate, and which deliverables are due. The Dashboard highlights engagement gaps, overdue actions, upcoming governance and RACI issues.
Stakeholder engagement levels
Level | Meaning
1 · Unaware | Doesn't yet know about the engagement or how it affects them.
2 · Resistant | Aware and opposed, or pushing for a conflicting outcome.
3 · Neutral | Aware but not actively supporting or opposing.
4 · Supportive | Aware and supports the approach and decisions.
5 · Leading | Actively champions the work and influences others.
Influence and interest quadrants
Quadrant | Approach
Manage closely | High influence, high interest. Involve in decisions; engage frequently and personally.
Keep satisfied | High influence, lower interest. Brief on decisions that affect them; avoid overloading.
Keep informed | Lower influence, high interest. Share progress regularly and use their feedback.
Monitor | Lower influence and interest. Light-touch updates; watch for changes.
The threshold for 'high' is set on the Stakeholder Register tab (default 4 on a 1–5 scale).
RACI
Code | Meaning
R · Responsible | Does the work. At least one per activity.
A · Accountable | Owns the outcome and makes the final decision. Exactly one per activity.
C · Consulted | Gives input before the decision; two-way conversation.
I · Informed | Told about the outcome; one-way communication.
R/A | Responsible and accountable (does the work and owns the decision).
How to maintain
1. Update current engagement, last contact and next action for each stakeholder after key interactions; review weekly with the Engagement Lead.
2. Re-score influence and interest at each phase change (for example before pilot and before each wave).
3. Keep RACI in step with the Change Log decision thresholds; the check column flags rows without exactly one A.
4. Update governance next dates and communication next send dates after each meeting or send.
Grey columns calculate automatically. Dashboard date windows use the reporting date above.
Version history
Version | Date | Author | Change summary
1.0 | 2026-09-10 | Bhawna | Initial engagement plan: 18 stakeholders, 18 RACI activities, 13 governance forums, 12 communications, 16 deliverables.

## Dashboard
Engagement Dashboard
Merchant Payment Operations & Dispute Hub · Simulation project · Figures update automatically
Reporting date: 10-Sep-2026
Summary
Stakeholders | Manage closely | With engagement gap | Resistant or unaware | Overdue stakeholder actions | Governance meetings in next 14 days | Deliverables in review | RACI rows to fix
18 | 5 | 14 | 3 | 1 | 10 | 4 | 0
Influence and interest map
Influence ↑ | Keep satisfied (4) |  |  | Manage closely (5)
Higher | Steering Committee (finance, technology and risk delegates) |  |  | Business Sponsor (Head of Merchant Services)
| InfoSec Lead |  |  | Dispute Ops Lead
| Data Governance Lead |  |  | Finance Lead
| Payment Processor Account Manager |  |  | Compliance Lead
Merchant Relationship Lead
| Monitor (6) |  |  | Keep informed (3)
Lower | Legal Counsel |  |  | Fraud Operations Lead
| IAM Team Lead |  |  | Pilot merchants (10)
| Data Engineering Lead |  |  | Delivery squads (Portal, Integration, Data)
Customer Servicing Lead
Marketing and Merchant Communications Lead
Document Storage Vendor
| Lower interest |  |  | Interest → | Higher interest
Biggest engagement gaps (gap × influence)
ID | Stakeholder | Current | Desired | Gap | Next action |  | Due
SH-05 | Fraud Operations Lead | Resistant | Supportive | 2 | Share CR-01 impact assessment and Phase 2 roadmap slot |  | 2026-09-11
SH-14 | Marketing and Merchant Communications Lead | Unaware | Supportive | 3 | First briefing on GTM plan |  | 2026-10-05
SH-17 | Pilot merchants (10) | Unaware | Supportive | 3 | Send pilot invitations once terms are approved |  | 2026-11-02
SH-01 | Business Sponsor (Head of Merchant Services) | Supportive | Leading | 1 | Pre-wire CR-01 Option C and business case before steering committee |  | 2026-09-14
SH-02 | Steering Committee (finance, technology and risk delegates) | Neutral | Supportive | 1 | Circulate pre-read two days before next meeting |  | 2026-09-22
SH-03 | Dispute Ops Lead | Supportive | Leading | 1 | Confirm UAT SME bookings for November |  | 2026-09-18
Governance in the next 14 days
Date | Forum |  | Chair | Decisions and outputs |  |  | Days until
2026-09-11 | Sprint review |  | Product Owner | Accepted stories; backlog changes |  |  | 1
2026-09-14 | Sponsor 1:1 |  | Engagement Lead | Medium-impact change decisions; escalation support |  |  | 4
2026-09-14 | Sprint planning |  | Product Owner | Sprint goal and committed items |  |  | 4
2026-09-15 | Backlog refinement |  | Product Owner | Refined and estimated stories |  |  | 5
2026-09-15 | Design authority |  | Tech Lead | Design sign-off (I-03); architecture decisions |  |  | 5
2026-09-15 | Processor vendor sync |  | Project Manager | Vendor actions and dates; escalation if dates slip |  |  | 5
2026-09-16 | Weekly status and RAID / change review |  | Project Manager | Owners and dates for actions; items to escalate |  |  | 6
2026-09-16 | Compliance and security checkpoint |  | Compliance Lead | Evidence gaps closed; compliance risks escalated |  |  | 6
2026-09-17 | Outcome definitions decision meeting |  | Business Sponsor | CR-05 decision; KPI-01 and KPI-02 status updated |  |  | 7
2026-09-24 | Steering Committee |  | Business Sponsor | Approve High-impact changes, go / no-go decisions, escalations |  |  | 14
Deliverables due in the next 30 days (not yet approved)
ID | Deliverable |  | Owner | Approver | Due | Status | Overdue?
DL-07 | Figma MVP designs |  | UX Designer | Design authority | 2026-09-15 | In Review | No
DL-11 | Stakeholder engagement plan |  | Product Owner and Engagement Lead | Business Sponsor | 2026-09-17 | In Review | No
DL-09 | KPI and metrics definitions |  | Product Owner | Business Sponsor | 2026-09-18 | In Review | No
DL-10 | Business case and GTM plan |  | Product Owner | Steering Committee | 2026-09-24 | In Review | No
Engagement health by stakeholder type
Type |  | Stakeholders | Manage closely | With gap | Resistant or unaware | Overdue actions
Client |  | 14 | 5 | 12 | 2 | 0
Vendor |  | 2 | 0 | 1 | 0 | 1
External |  | 1 | 0 | 1 | 1 | 0
Delivery partner |  | 1 | 0 | 0 | 0 | 0

## Engagement Overview
Engagement Overview
Merchant Payment Operations & Dispute Hub · Simulation project
Engagement summary
Topic | Summary
Client context | Merchant services division of a card payments provider (illustrative), supporting about 25,000 active merchants.
Problem | Merchants manage disputes by email and spreadsheets. Deadlines are missed, evidence is chased manually, ops handling time is high and settlement changes are hard to explain.
Objectives | 1. Give merchants self-service dispute tracking and evidence submission. 2. Cut ops handling time and missed-deadline losses. 3. Keep card data out of evidence storage. 4. Give ops and finance one trusted set of dispute numbers.
In scope (MVP) | Merchant portal (inbox, dispute detail, evidence upload and submission), processor integration, reminders, settlement visibility, ops work queue, reporting, servicing status API.
Out of scope | Fraud case management (Phase 2, CR-01), Spanish portal (Phase 2, CR-04), marketplace sub-merchant model, SMS reminders pending CR-09.
Delivery approach | Agile delivery in two-week sprints with a pilot-led rollout; governance through sponsor 1:1s, fortnightly steering committee and weekly RAID and change review.
Key constraints | Q4 dispute peak limits SME time (R-06); holiday change freeze after go-live; security and compliance gates before launch (D-03, CR-03).
Success criteria | MVP live by 11-Dec-2026; pilot exit gates met; base-case KPI targets by mid-2027 (KPI-03 on-time response 95%, KPI-05 handling time 25 min, KPI-06 portal share 70%).
Phases
Phase | Dates | Focus | Key outputs
Discovery | Jun – Jul 2026 | Merchant and ops research; problem and opportunity sizing | Discovery findings; MVP scope baseline
Mobilization and design | Jul – Aug 2026 | Team setup, solution design, governance, RAID and change control | Solution design; RAID and change logs; engagement plan
Build | 20-Jul – 04-Dec 2026 | Sprints 1–10; SIT, security and accessibility testing; UAT | Working MVP; RTM; KPI definitions; business case
Launch and pilot | Dec 2026 – Mar 2027 | Go-live, hypercare, 10-merchant pilot | Go-live readiness pack; pilot results report
Scale | Mar – Dec 2027 | Wave 1, Wave 2, general availability; email intake retirement | Wave go / no-go packs; benefits tracking
Engagement team model
Role | Organization | Responsibilities |  | Allocation
Business Sponsor | Client | Funding, priorities, Medium-impact decisions, sponsor escalations |  | As needed
Engagement Lead | Delivery partner | Overall delivery accountability, sponsor relationship, commercial and quality oversight |  | Part time
Product Owner | Delivery partner | Product vision, backlog ownership, stakeholder alignment, acceptance, KPIs and business case |  | Full time
Project Manager | Delivery partner | Plan, RAID, change control, status reporting, vendor coordination |  | Part time
Business Analyst | Delivery partner | Requirements, process mapping, acceptance criteria, UAT support |  | Full time
Tech Lead | Delivery partner | Solution design, engineering delivery, technical risk |  | Full time
Delivery squads (Portal, Integration, Data) | Delivery partner | Build, test and release MVP features |  | Full time
QA Lead | Delivery partner | Test strategy, traceability, UAT coordination |  | Full time
UX Designer | Delivery partner | Research, designs, accessibility |  | Part time
Client SMEs (Dispute Ops, Finance, Compliance, Servicing) | Client | Process knowledge, requirement sign-off, UAT execution, readiness |  | Part time (bookings agreed)

## Stakeholder Register
Stakeholder Register
Merchant Payment Operations & Dispute Hub · Simulation project · Stakeholders are roles, not named individuals
High influence / interest threshold (1–5): |  |  |  | 4 |  | Grey columns calculate automatically. Engagement gap = desired level − current level.
ID | Stakeholder | Group | Type | Influence (1-5) | Interest (1-5) | Quadrant | Current engagement | Desired engagement | Gap | Priority score | Interests and concerns | Engagement strategy | Relationship owner | Frequency | Channel | Linked items | Last contact | Next action | Next action date | Action overdue? | h_mc | h_ks | h_ki | h_mon | h_gap
SH-01 | Business Sponsor (Head of Merchant Services) | Merchant Services leadership | Client | 5 | 4 | Manage closely | Supportive | Leading | 1 | 5 | Return on investment, go-live date, merchant experience, visible progress for leadership. | Weekly 1:1; pre-wire every steering committee decision; share business case scenarios early so there are no surprises. | Engagement Lead | Weekly | 1:1 meeting | CR-01, CR-05, Business case | 2026-09-07 | Pre-wire CR-01 Option C and business case before steering committee | 2026-09-14 | No | 5 |  |  |  | 5.0099
SH-02 | Steering Committee (finance, technology and risk delegates) | Executive governance | Client | 5 | 3 | Keep satisfied | Neutral | Supportive | 1 | 5 | Cost against contingency, security and compliance risk, delivery confidence. | Fortnightly decision papers with clear options and recommendation; show conservative case openly; escalate only decisions that need them. | Product Owner | Fortnightly | Steering committee | D-03, CR-06, Business case | 2026-09-10 | Circulate pre-read two days before next meeting | 2026-09-22 | No |  | 6 |  |  | 5.0099
SH-03 | Dispute Ops Lead | Dispute Operations | Client | 4 | 5 | Manage closely | Supportive | Leading | 1 | 4 | Team workload during Q4 peak, handling time, reliable deadlines for merchants. | Co-design sessions; make them owner of UAT scenarios and ops readiness; protect SME time during peak (R-06). | Product Owner | Weekly | Working session | R-06, KPI-05, I-02 | 2026-09-09 | Confirm UAT SME bookings for November | 2026-09-18 | No | 7 |  |  |  | 4.0099
SH-04 | Finance Lead | Finance | Client | 4 | 4 | Manage closely | Neutral | Supportive | 1 | 4 | How dispute outcomes and win rate are defined; whether ops savings are cashable; reconciliation accuracy. | 1:1 using the outcome definitions worked example; involve in KPI sign-off; agree ops capacity treatment before Wave 1. | Product Owner | Weekly | 1:1 meeting | CR-05, I-05, LR-17 | 2026-09-08 | Walk through outcome definitions worked example | 2026-09-15 | No | 8 |  |  |  | 4.0099
SH-05 | Fraud Operations Lead | Fraud Operations | Client | 3 | 4 | Keep informed | Resistant | Supportive | 2 | 6 | Wants fraud case management in the MVP; worried fraud context will be missed on disputes. | Explain CR-01 options and impact; offer Option C read-only reference in MVP with a Phase 2 roadmap commitment; invite to sprint review. | Product Owner | Fortnightly | Working session | CR-01, D-07, R-07 | 2026-09-03 | Share CR-01 impact assessment and Phase 2 roadmap slot | 2026-09-11 | No |  |  | 9 |  | 6.0099
SH-06 | Compliance Lead | Compliance | Client | 5 | 4 | Manage closely | Supportive | Supportive | 0 | 0 | PCI DSS scope, card data exposure, evidence retention, audit trail. | Fortnightly checkpoint using the RTM control view; share evidence gaps early; no surprises at go-live. | Product Owner | Fortnightly | Checkpoint meeting | R-02, CR-03, A-07, CTL-09 | 2026-09-02 | Review CTL-09 retention gap and A-07 timeline | 2026-09-16 | No | 10
SH-07 | InfoSec Lead | Information Security | Client | 4 | 3 | Keep satisfied | Neutral | Supportive | 1 | 4 | Pen test capacity, redaction validation effort, vendor security assessments. | Share test scope and dates early; ask sponsor to support priority pen test slot; agree redaction validation test set. | Project Manager | Fortnightly | Checkpoint meeting | D-03, LR-02, LR-03, R-08 | 2026-09-04 | Request priority pen test slot with sponsor support | 2026-09-14 | No |  | 11 |  |  | 4.0099
SH-08 | Legal Counsel | Legal | Client | 3 | 2 | Monitor | Neutral | Supportive | 1 | 3 | Merchant portal terms of use, data retention obligations. | Book a fixed review slot with a short pre-read highlighting only decisions needed. | Product Owner | Monthly | Email and meeting | D-05, A-07 | 2026-09-08 | Confirm legal review slot for terms of use | 2026-09-17 | No |  |  |  | 12 | 3.0099
SH-09 | IAM Team Lead | Identity and Access Management | Client | 3 | 2 | Monitor | Supportive | Supportive | 0 | 0 | Role configuration effort and timing. | Keep the Tuesday joint checkpoint; confirm acceptance criteria for role setup. | Tech Lead | Weekly | Checkpoint meeting | D-02, A-03 | 2026-09-08 | Confirm role configuration on track for 30-Sep | 2026-09-15 | No |  |  |  | 13
SH-10 | Data Engineering Lead | Data Engineering | Client | 3 | 3 | Monitor | Neutral | Supportive | 1 | 3 | Pipeline capacity, data quality rules, ownership of settlement data issues. | Agree data quality acceptance rules and exception ownership; include in sprint reviews for reporting stories. | Tech Lead | Fortnightly | Working session | D-04, R-05, US-033 | 2026-09-01 | Agree pipeline acceptance rules | 2026-09-21 | No |  |  |  | 14 | 3.0099
SH-11 | Data Governance Lead | Data Governance | Client | 4 | 2 | Keep satisfied | Neutral | Supportive | 1 | 4 | Personal data in analytics events; approval workload. | Walk through a privacy-first tracking plan with no personal or card data; ask for conditional approval to unblock pilot metrics. | Product Owner | Monthly | Governance forum | I-06, CTL-04, KPI-08 | 2026-09-08 | Present revised tracking plan for approval | 2026-10-01 | No |  | 15 |  |  | 4.0099
SH-12 | Customer Servicing Lead | Customer Servicing | Client | 3 | 3 | Monitor | Neutral | Supportive | 1 | 3 | Agent training time, call volumes after launch, status API readiness. | Include in readiness huddles from November; share servicing API demo; co-write call scripts. | Product Owner | Monthly | Readiness huddle | D-06, LR-09, KPI-07 | 2026-08-27 | Invite to Sprint 8 review for status API demo | 2026-10-26 | No |  |  |  | 16 | 3.0098
SH-13 | Merchant Relationship Lead | Merchant Relationships | Client | 4 | 4 | Manage closely | Supportive | Leading | 1 | 4 | Merchant pushback on change, pilot recruitment, language needs. | Co-own the GTM plan and pilot recruitment; give RMs an enablement pack and early demo access. | Product Owner | Weekly | Working session | LR-10, LR-13, CR-04 | 2026-09-09 | Finalize pilot merchant list | 2026-09-25 | No | 17 |  |  |  | 4.0098
SH-14 | Marketing and Merchant Communications Lead | Marketing | Client | 2 | 3 | Monitor | Unaware | Supportive | 3 | 6 | Communication lead times, brand approval, channel choice. | Brief on GTM plan and communications calendar; agree approval lead times. | Merchant Relationship Lead | Monthly | Briefing | LR-11, LR-12 |  | First briefing on GTM plan | 2026-10-05 | No |  |  |  | 18 | 6.0098
SH-15 | Payment Processor Account Manager | Processor (vendor) | Vendor | 4 | 3 | Keep satisfied | Neutral | Supportive | 1 | 4 | Sandbox stability, production access timelines, integration support effort. | Weekly vendor call with tracked actions; escalate through sponsor if production access slips further. | Project Manager | Weekly | Vendor call | D-01, I-01, A-02 | 2026-09-08 | Escalate sandbox status defect and production access date | 2026-09-15 | No |  | 19 |  |  | 4.0098
SH-16 | Document Storage Vendor | Storage vendor | Vendor | 2 | 2 | Monitor | Neutral | Neutral | 0 | 0 | Completing the third-party risk assessment. | Send questionnaire and SOC 2 request early; monitor only. | Tech Lead | As needed | Email | R-08 | 2026-09-03 | Chase security questionnaire | 2026-09-09 | Overdue |  |  |  | 20
SH-17 | Pilot merchants (10) | Merchants | External | 2 | 5 | Keep informed | Unaware | Supportive | 3 | 6 | Ease of use, time saved, confidence their deadlines are safe. | White-glove onboarding, weekly feedback calls during pilot, visible changes made from their feedback. | Merchant Relationship Lead | Weekly during pilot | Onboarding and feedback calls | A-01, R-04, KPI-08 |  | Send pilot invitations once terms are approved | 2026-11-02 | No |  |  | 21 |  | 6.0098
SH-18 | Delivery squads (Portal, Integration, Data) | Delivery team | Delivery partner | 3 | 5 | Keep informed | Supportive | Supportive | 0 | 0 | Clear priorities, fast unblocking, stable scope. | Sprint ceremonies; blockers raised daily and tracked in RAID; explain every scope change and why. | Product Owner | Daily | Stand-up and sprint ceremonies | I-01, R-07 | 2026-09-10 | Sprint 4 review and retrospective | 2026-09-11 | No |  |  | 22

## RACI Matrix
RACI Matrix
Merchant Payment Operations & Dispute Hub · Simulation project · Decision rights align with Change Log thresholds
Use R, A, C, I or R/A. Each activity needs exactly one A and at least one R; the Check column flags problems.
ID | Activity or decision | Area | Business Sponsor | Steering Committee | Engagement Lead | Product Owner | Project Manager | Tech Lead | Dispute Ops Lead | Finance Lead | Compliance Lead | InfoSec Lead | Legal Counsel | Data Governance Lead | Merchant Relationship Lead | Servicing Lead | A count | R count | Check
RA-01 | Approve MVP scope baseline | Scope | A | I | C | R | C | C | C | C | C |  |  |  | C |  | 1 | 1 | OK
RA-02 | Prioritize and order the product backlog | Scope | C |  |  | R/A | I | C | C | [7 empty] | 1 | 1 | OK
RA-03 | Approve Low-impact change requests | Scope: Change control; A: I; R: R/A; C: I; C: C | [5 empty] | 1 | 1 | OK
RA-04 | Approve Medium-impact change requests | Change control | A | I |  | R | C | C |  | C | [6 empty] | 1 | 1 | OK
RA-05 | Approve High-impact and compliance change requests | Change control | C | A | C | R | C | C |  | C | C | [5 empty] | 1 | 1 | OK
RA-06 | Maintain RAID log and escalate risks | Governance | I | I | C | R | A | R | [8 empty] | 1 | 2 | OK
RA-07 | Approve compliance controls and evidence | Scope: Compliance; R: R; C: R; C: A | C | C | C |  |  | 1 | 2 | OK
RA-08 | Security sign-off for go-live | Compliance |  | I |  | I | I | R |  |  | C | A |  |  |  |  | 1 | 1 | OK
RA-09 | Approve analytics tracking plan | Scope: Data; R: R; C: C; C: C |  |  | A |  |  | 1 | 1 | OK
RA-10 | Approve KPI and dispute outcome definitions | Data | A | I |  | R |  |  | C | C |  |  |  | C |  |  | 1 | 1 | OK
RA-11 | Execute user acceptance testing | Quality |  |  |  | A | C | C | R | R | [5 empty] | C | 1 | 2 | OK
RA-12 | Sign off user acceptance testing | Quality | A |  |  | R | I |  | R | R | C | [5 empty] | 1 | 3 | OK
RA-13 | Go-live and pilot go / no-go decision | Launch | R | A | C | R | R | C | C |  | C | C |  |  | C |  | 1 | 3 | OK
RA-14 | Merchant communications and pilot recruitment | Scope: Launch; A: I; R: C; C: C |  | C |  | R/A |  | 1 | 1 | OK
RA-15 | Servicing readiness and agent training | Scope: Launch; R: C; C: I; C: C |  |  |  |  | R/A | 1 | 1 | OK
RA-16 | Business case and benefits tracking | Value | A | I | C | R |  |  | C | C | [6 empty] | 1 | 1 | OK
RA-17 | Weekly status reporting | Governance | I | I | C | C | R/A | [9 empty] | 1 | 1 | OK
RA-18 | Vendor and third-party escalations | Governance | A |  | C | I | R | R | [8 empty] | 1 | 2 | OK
| Accountable for (count) |  | 6 | 2 | 0 | 3 | 2 | 0 | 0 | 0 | 1 | 1 | 0 | 1 | 1 | 1
| Responsible for (count) |  | 3 | 2 | 2 | 14 | 5 | 6 | 4 | 4 | 2 | 2 | 2 | 2 | 3 | 3
Role load helps spot overload: a role accountable for many decisions may slow the engagement down.

## Governance
Governance & Escalation
Merchant Payment Operations & Dispute Hub · Simulation project · Decision forums, cadence and escalation path
Update Next date after each meeting. Grey column shows days until the next meeting from the reporting date.
Forum | Purpose | Chair | Attendees | Frequency | Day and time | Inputs | Decisions and outputs | Next date | Days until | h_next
Steering Committee | Make High-impact decisions; track delivery confidence, budget and compliance risk. | Business Sponsor | Steering Committee delegates, Engagement Lead, Product Owner, Project Manager | Fortnightly | Thursday 16:00 | Decision papers, RAID top risks, change log, business case | Approve High-impact changes, go / no-go decisions, escalations | 2026-09-24 | 14 | 2026-09-24
Sponsor 1:1 | Pre-wire decisions and keep the sponsor ahead of issues. | Engagement Lead | Business Sponsor, Product Owner | Weekly | Monday 09:30 | Upcoming decisions, stakeholder issues | Medium-impact change decisions; escalation support | 2026-09-14 | 4 | 2026-09-14
Weekly status and RAID / change review | Review progress, RAID items and pending change requests. | Project Manager | Product Owner, Tech Lead, workstream leads | Weekly | Wednesday 11:00 | Status report, RAID log, change log | Owners and dates for actions; items to escalate | 2026-09-16 | 6 | 2026-09-16
Sprint review | Demo the increment and gather stakeholder feedback. | Product Owner | Delivery squads, Dispute Ops Lead, Finance Lead, interested stakeholders | Every 2 weeks | Friday 14:00 (sprint end) | Done stories, sprint goal | Accepted stories; backlog changes | 2026-09-11 | 1 | 2026-09-11
Sprint planning | Agree sprint goal and commitment. | Product Owner | Delivery squads, Tech Lead | Every 2 weeks | Monday 10:00 (sprint start) | Ready backlog items, capacity | Sprint goal and committed items | 2026-09-14 | 4 | 2026-09-14
Backlog refinement | Keep the next two sprints Ready. | Product Owner | Tech Lead, BA, squad representatives, SMEs as needed | Weekly | Tuesday 14:00 | Upcoming stories, designs, dependencies | Refined and estimated stories | 2026-09-15 | 5 | 2026-09-15
Design authority | Approve designs and architecture decisions. | Tech Lead | Product Owner, UX Designer, InfoSec Lead, Dispute Ops Lead | Fortnightly | Tuesday 16:00 | Figma designs, solution design changes | Design sign-off (I-03); architecture decisions | 2026-09-15 | 5 | 2026-09-15
Compliance and security checkpoint | Track controls, evidence and security testing. | Compliance Lead | InfoSec Lead, Legal Counsel, Product Owner, QA Lead | Fortnightly | Wednesday 15:00 | RTM control view, test results, pen test plan | Evidence gaps closed; compliance risks escalated | 2026-09-16 | 6 | 2026-09-16
Outcome definitions decision meeting | Decide how dispute outcomes and win rate are defined (CR-05). | Business Sponsor | Finance Lead, Dispute Ops Lead, Product Owner | One-off | Thursday 10:00 | KPI outcome definitions worked example, CR-05 | CR-05 decision; KPI-01 and KPI-02 status updated | 2026-09-17 | 7 | 2026-09-17
Data governance forum | Approve data use, analytics tracking and data quality rules. | Data Governance Lead | Product Owner, Data Engineering Lead, Compliance Lead | Monthly | First Thursday 13:00 | Tracking plan, data dictionary | Tracking plan approval (I-06) | 2026-10-01 | 21
Processor vendor sync | Resolve sandbox issues and track production access. | Project Manager | Processor account manager, Tech Lead | Weekly | Tuesday 17:00 | Vendor action log, defects | Vendor actions and dates; escalation if dates slip | 2026-09-15 | 5 | 2026-09-15
Ops and servicing readiness huddle | Prepare dispute ops and servicing for launch. | Dispute Ops Lead | Servicing Lead, Product Owner, trainers | Weekly from November | Monday 15:00 | Launch readiness checklist | Training and process readiness actions | 2026-11-02 | 53
Pilot merchant feedback call | Hear pilot merchant experience and track exit gates. | Merchant Relationship Lead | Pilot merchants, Product Owner | Weekly during pilot | Friday 11:00 | Pilot KPIs, feedback log | Backlog changes; pilot issues escalated | 2027-01-15 | 127
Escalation path
Level | Escalate to | Trigger |  | How |  | Response time
Level 1 | Workstream owner | Issue can be resolved within the team or sprint |  | Owner resolves and records in RAID |  | 2 business days
Level 2 | Product Owner and Project Manager | Affects a sprint goal, a cross-team dependency or a Low-impact change |  | Raised at weekly status and RAID / change review |  | 3 business days
Level 3 | Business Sponsor | Medium-impact change; dependency slip threatening a milestone; unresolved stakeholder conflict |  | Raised at sponsor 1:1 with options and a recommendation |  | 5 business days
Level 4 | Steering Committee | High-impact change; go-live, budget beyond contingency or compliance at risk |  | Decision paper at next steering committee, or ad hoc meeting within 48 hours if critical |  | Next meeting or 48 hours
Formulas:
h_next = IF(AND([Next date]<>"",N([Days until])>=0,N([Days until])<=14),[Next date]+ROW()/100000,"")

## Communication Plan
Communication Plan
Merchant Payment Operations & Dispute Hub · Simulation project
Update Next send date and Status after each communication.
ID | Communication | Audience | Purpose | Owner | Channel | Frequency | Artifact | Next send date | Status | Due in (days)
CM-01 | Weekly status report | Business Sponsor, steering committee delegates, workstream leads | Progress, RAG status, top risks and decisions needed | Project Manager | Email and Confluence | Weekly (Friday) | One-page status report | 2026-09-11 | Active | 1
CM-02 | Steering committee pack | Steering Committee | Decisions with options, business case view, top RAID items | Product Owner and Project Manager | Pre-read and meeting | Fortnightly | Decision paper and short deck | 2026-09-22 | Active | 12
CM-03 | Sprint review demo | Business stakeholders, dispute ops, finance | Show working software and collect feedback | Product Owner | Live demo | Every 2 weeks | Demo and review notes | 2026-09-11 | Active | 1
CM-04 | RAID and change digest | Workstream leads | New or escalated items and pending decisions | Project Manager | Confluence page and Slack | Weekly | RAID and change log extract | 2026-09-16 | Active | 6
CM-05 | Decision memo: dispute outcome definitions | Finance Lead, Dispute Ops Lead, Business Sponsor | Present CR-05 options and recommendation | Product Owner | Memo and meeting | One-off | Decision memo with worked example | 2026-09-15 | In Preparation | 5
CM-06 | Compliance and security update | Compliance Lead, InfoSec Lead, Legal Counsel | Control status and evidence gaps | Product Owner | Checkpoint meeting | Fortnightly | RTM control assurance view | 2026-09-16 | Active | 6
CM-07 | Delivery team updates | Delivery squads | Priorities, blockers and scope changes | Product Owner | Stand-up and Slack | Daily | Sprint board | 2026-09-11 | Active | 1
CM-08 | Ops and servicing readiness bulletin | Dispute ops analysts, servicing agents | Training dates and process changes | Dispute Ops Lead and Servicing Lead | Email and huddle | Weekly from November | Readiness bulletin | 2026-11-02 | Planned | 53
CM-09 | Relationship manager briefing | Relationship managers | Pilot plan, messaging and objection handling | Merchant Relationship Lead | Team meeting | Monthly, weekly from November | RM enablement pack | 2026-10-01 | Planned | 21
CM-10 | Pilot merchant invitation and onboarding | Pilot merchants | Invitation, what to expect and how to start | Merchant Relationship Lead and Marketing Lead | Email and onboarding call | One-off, then weekly during pilot | Invitation and welcome emails; onboarding guide | 2026-12-07 | Planned | 88
CM-11 | Pilot results report | Business Sponsor, Steering Committee | Exit gate results and Wave 1 recommendation | Product Owner | Report and steering committee | Once at pilot end | Pilot results report | 2027-03-11 | Planned | 182
CM-12 | Vendor escalation note | Processor account manager | Production access and sandbox defect escalation | Project Manager | Email and vendor call | As needed | Escalation note with dates and impact | 2026-09-15 | In Preparation | 5

## Deliverables
Deliverables & Milestones
Merchant Payment Operations & Dispute Hub · Simulation project
Update Status as deliverables move through review and approval.
ID | Deliverable | Phase | Description | Owner | Approver | Due date | Status | Linked artifact | Overdue? | h_due
DL-01 | Discovery findings and problem statement | Discovery | Merchant and ops pain points, current process, opportunity sizing | Product Owner | Business Sponsor | 2026-07-10 | Approved | Discovery pack | No
DL-02 | MVP scope baseline | Discovery | Agreed MVP scope, out-of-scope items and assumptions | Product Owner | Business Sponsor | 2026-07-17 | Approved | Product_Backlog workbook | No
DL-03 | Solution design | Mobilization and design | Architecture, integrations, data model and security design | Tech Lead | Design authority | 2026-08-14 | Approved | Solution design document | No
DL-04 | RAID log | Mobilization and design | Risks, assumptions, issues and dependencies with owners | Project Manager | Business Sponsor | 2026-08-21 | Live document | RAID_Log workbook | No
DL-05 | Change log | Mobilization and design | Change requests, impact assessments and decisions | Project Manager | Business Sponsor | 2026-08-21 | Live document | Change_Log workbook | No
DL-06 | Product backlog, epics and sprint plan | Build | Ordered backlog with acceptance criteria and sprint plan | Product Owner | Business Sponsor | 2026-07-17 | Live document | Product_Backlog workbook | No
DL-07 | Figma MVP designs | Build | Merchant inbox, dispute detail and evidence upload screens | UX Designer | Design authority | 2026-09-15 | In Review | Figma file (I-03) | No | 2026-09-15
DL-08 | Requirements traceability matrix | Build | Requirements traced to stories, tests, defects and controls | Product Owner and QA Lead | Compliance Lead | 2026-09-10 | Live document | RTM workbook | No
DL-09 | KPI and metrics definitions | Build | Metric catalog, outcome definitions and data dictionary | Product Owner | Business Sponsor | 2026-09-18 | In Review | KPI_Definitions workbook | No | 2026-09-18
DL-10 | Business case and GTM plan | Build | Three-scenario business case, rollout plan and launch readiness | Product Owner | Steering Committee | 2026-09-24 | In Review | Business_Case_GTM workbook | No | 2026-09-24
DL-11 | Stakeholder engagement plan | Build | Stakeholder register, RACI, governance and communications | Product Owner and Engagement Lead | Business Sponsor | 2026-09-17 | In Review | This workbook | No | 2026-09-17
DL-12 | UAT plan and scripts | Build | UAT scope, entry and exit criteria, scripts and schedule | QA Lead | Business Sponsor | 2026-10-30 | Not Started | RTM workbook (UAT test cases) | No
DL-13 | Go-live readiness pack | Launch | Launch readiness evidence for go / no-go | Project Manager | Steering Committee | 2026-12-04 | Not Started | Business_Case_GTM workbook (Launch Readiness) | No
DL-14 | Hypercare exit and BAU handover plan | Launch | Support model, runbooks and ownership after hypercare | Project Manager | Dispute Ops Lead | 2027-01-22 | Not Started |  | No
DL-15 | Pilot results report | Pilot | Pilot exit gate results and recommendation | Product Owner | Steering Committee | 2027-03-11 | Not Started | KPI_Definitions workbook | No
DL-16 | Wave 1 go / no-go pack | Scale | Readiness and business case refresh for Wave 1 | Product Owner | Steering Committee | 2027-03-12 | Not Started | Business_Case_GTM workbook | No
Formulas:
h_due = IF(AND([Due date]<>"",[Status]<>"Approved",[Status]<>"Live document",[Due date]<=Cover!$C7+30),[Due date]+ROW()/100000,"")