## Slide 1
PRODUCT & PROGRAM EXECUTIVE REVIEW
Merchant Payment Operations
& Dispute Hub
MVP business case, delivery status, and the decisions leadership needs to make now
PREPARED BY
Bhawna, Product Owner
KEY DOCUMENTS
PRD v1.2 · Roadmap v1.1
STATUS AS OF
10 September 2026
PLANNED GO-LIVE
11 December 2026
Simulation project: a Product Owner portfolio exercise. Not an actual client system; all figures are illustrative.
Notes: Frame this as a simulation built to show the full Product Owner lifecycle. The deck covers why the product matters, where delivery stands, the investment case, and five decisions leadership needs to make.

## Slide 2
THE PROBLEM
Disputes run on email, deadlines get missed, and no one trusts the numbers
Section 1 of 3 · The problem, the market and the solution
Merchant Payment Operations & Dispute Hub · Simulation project
78%
On-time merchant response rate today
Target 95% · KPI-03
9%
Of closed disputes lost only because the deadline passed
Target 3% · KPI-04
42 min
Dispute Ops handling time per dispute
Target 25 min · KPI-05
100%
Of evidence still arrives by email
Target 70% via portal · KPI-06
Underneath the numbers
Card numbers sit unmanaged in email attachments: an active PCI DSS exposure (R-02)
Finance and Dispute Ops calculate win rate differently: 40% vs 62.5% on the same 100 disputes (I-05)
Merchants can't see how disputes affect their payouts, so they contact servicing: 14 settlement queries per 100 merchants a month (KPI-07)
Notes: Lead with the missed-deadline loss: 9% of closed disputes are lost on process, not merits. The win-rate disagreement is why a single outcome definition (CR-05) is on the decision list.

## Slide 3
THE SOLUTION
One self-service portal replaces the email-and-spreadsheet workflow
Section 1 of 3 · The problem, the market and the solution
Merchant Payment Operations & Dispute Hub · Simulation project
A portal where merchants track disputes, get deadline reminders and submit evidence online, so they stop losing disputes to missed deadlines and Dispute Ops stops processing everything by email.
TODAY
WITH THE DISPUTE HUB
Notice: Email from Ops, sometimes missed
Notice: Dispute appears in the inbox with its due date; reminders at 5 and 2 days
Understand: Look up the reason code or call servicing
Understand: Plain-language reason with the evidence that usually wins
Gather evidence: Collect files and email them to Ops
Gather evidence: Upload files; card numbers are redacted automatically
Respond: Ops re-keys evidence into the processor
Respond: Submit in one step, or accept with a clear warning
Track: Chase Ops by email or phone
Track: Status and 'last synced' time always visible
Notes: Walk one dispute through both columns. The biggest changes are deadline visibility, guided evidence and redaction on upload.

## Slide 4
THE MARKET
Dispute portals are table stakes; our edge is prevention and explainable AI
What discovery found, and how the Dispute Hub positions itself
Section 1 of 3 · The problem, the market and the solution
Merchant Payment Operations & Dispute Hub · Simulation project
What the market already offers
American Express
Online Disputes tool: see open and urgent disputes, upload documents, respond online, email alerts, reply-by dates
Adyen
Disputes list showing days left to defend and the latest event
Stripe
Smart Disputes builds evidence packets and submits them before the deadline if the merchant does nothing
Razorpay
Dashboard to accept or contest disputes with typed evidence, plus webhook updates
Where the Dispute Hub differentiates
MVP STRENGTHS
Card numbers redacted on upload, with quarantine
Settlement debits and reversals linked to disputes
One agreed outcome definition for Finance and Ops
Internal Ops workbench and feed-health alerts
BEYOND MVP (PROPOSED)
Next
Dispute ratio health, pre-dispute alerts, AI evidence copilot with human review
Later
Friendly fraud automation, root-cause insights, AI agent purchase readiness
Sources: Discovery & Decision Log v2.0 (DSC-06 to DSC-15; SRC-01 to SRC-20), accessed 11 Sep 2026. Positioning is for the simulation, not a claim about any provider’s plans.
Notes: Be explicit that Amex already runs an online disputes tool. The hub is positioned as network-agnostic, and it differentiates through prevention and explainable AI rather than the portal itself.

## Slide 5
SCOPE
MVP scope at a glance
Section 1 of 3 · The problem, the market and the solution
Merchant Payment Operations & Dispute Hub · Simulation project
9
Epics
42
Backlog items
252
Story points
10
Two-week sprints
11 Dec 2026
Planned go-live
Nine MVP epics
EP-01 Merchant Access & Onboarding
28 pts
EP-02 Dispute Inbox & Tracking
32 pts
EP-03 Evidence Submission
45 pts
EP-04 Processor Integration
47 pts
EP-05 Notifications & Reminders
10 pts
EP-06 Settlement Visibility
19 pts
EP-07 Reporting & Analytics
23 pts
EP-08 Internal Ops Workbench
8 pts
EP-09 Platform Quality & Compliance
40 pts
Explicitly out of MVP scope
Fraud case management in the hub (a read-only reference is pending CR-01) · Spanish portal · SMS reminders · Marketplace sub-merchants · Reason code admin screen · Nightly data files · Automated dispute decisions · Prevention and AI capabilities (roadmap RM-25 to RM-30)
Notes: Scope is protected through change control. Everything in the amber box has a home on the roadmap or a recorded decision.

## Slide 6
DELIVERY STATUS
Sprint 4 of 10: 32% of MVP points complete
As of 10 September 2026 · 80 of 252 points · Sprints 1–3 delivered 69 of 69 planned points · 2 items blocked
Section 2 of 3 · Business case and delivery
Merchant Payment Operations & Dispute Hub · Simulation project
Chart: 
| EP-08 Internal Ops Workbench | EP-02 Dispute Inbox & Tracking | EP-09 Platform Quality & Compliance | EP-04 Processor Integration | EP-01 Merchant Access & Onboarding | EP-03 Evidence Submission | EP-05 Notifications & Reminders | EP-06 Settlement Visibility | EP-07 Reporting & Analytics
% complete | 100 | 84 | 48 | 34 | 18 | 11 | 0 | 0 | 0
Watch items
US-019 blocked
Status-update webhooks blocked by a processor sandbox issue (I-01)
US-034 blocked
Amplitude tracking waits for data governance approval (I-06)
Evidence Submission at 11%
Largest remaining epic (45 pts), most exposed to the December go-live
3 epics not started
Notifications, Settlement Visibility, Reporting & Analytics: 52 pts
Notes: Early sprints hit plan. The remaining work holds the riskiest capabilities: evidence submission, processor integration and the three unstarted epics.

## Slide 7
BUSINESS CASE
Base case is positive, but adoption and Ops capacity decide the outcome
Section 2 of 3 · Business case and delivery
Merchant Payment Operations & Dispute Hub · Simulation project
Chart: 3-year NPV by scenario
| Conservative | Base | Optimistic
3-year NPV ($k) | -839 | 149 | 1343
 | Conservative | Base | Optimistic
3-year NPV | ($839k) | $149k | $1.34M
3-year ROI | (59%) | 26% | 138%
Payback after go-live | Beyond 3 yrs | 2.3 yrs | 1.2 yrs
Year 3 net cash flow | ($13k) | $477k | $1.05M
$612k
One-time investment: build team, contingency, penetration test and accessibility audit
Conservative case loses money
Low adoption and redeployed rather than cashable capacity push NPV to ($839k). That is why the pilot gates and LR-17 matter.
Notes: Showing a negative conservative case makes the model credible. It also points leadership at the two assumptions that matter: adoption and how released capacity is treated.

## Slide 8
WHERE THE VALUE COMES FROM
85% of base-case benefit is released Ops capacity: confirm whether it is cashable
Section 2 of 3 · Business case and delivery
Merchant Payment Operations & Dispute Hub · Simulation project
Chart: Base case, 3-year benefits by source
| Released Ops capacity (hard) | Fewer servicing contacts (hard) | Retention and lower write-offs (soft)
3-year benefit ($k) | 1421 | 193 | 62
$1.68M vs $1.33M
Three-year benefits vs three-year costs (base case)
$771k a year
Merchant value at Year 3: money recovered or kept by merchants. Excluded from NPV.
Decision by 30 Oct
Finance Lead to confirm cashable vs redeployed capacity (LR-17)
How the value is created
Deadline visibility
→
More on-time responses
→
Fewer disputes lost
→
Less manual Ops work
→
Positive economics
Notes: Hard benefits are counted only at the cashable share. Soft benefits are confidence-discounted. Merchant value strengthens the adoption story but stays out of the provider NPV.

## Slide 9
SUCCESS METRICS
Success metrics: end-2027 checkpoint and steady-state targets
Interim values follow the quarterly benefits path in the Post-Launch Plan, which rolls up to the base business case
Section 2 of 3 · Business case and delivery
Merchant Payment Operations & Dispute Hub · Simulation project
Metric | Baseline | End of 2027 | Steady-state target | KPI
On-time response rate | 78% | 91% | 95% by end-2028 | KPI-03
Missed-deadline loss rate | 9% | 5% | 3% by end-2028 | KPI-04
Ops handling time per dispute | 42 min | 29 min | 25 min by end-2028 | KPI-05
Portal evidence share | 0% | 55% | 70% by 2029 | KPI-06
Settlement contacts per 100 merchants | 14 | 10 | 8 by end-2028 | KPI-07
Dispute value recovery (North Star, pending CR-05) | 38% | 42% | 45% by end-2028 | KPI-01
Guardrails and leading indicator
0
Card data exposure incidents · KPI-16
≤ 5 min
Status sync latency, 95th percentile · KPI-12
≤ 0.5%
Settlement reconciliation variance · KPI-15
≥ 60%
Pilot merchant activation · KPI-08
Notes: Earlier drafts showed steady-state targets as end-2027 goals. This version separates the realistic end-2027 checkpoint from the steady-state target.

## Slide 10
GO-TO-MARKET
Pilot-led rollout: each wave starts only when its gates are met
Section 2 of 3 · Business case and delivery
Merchant Payment Operations & Dispute Hub · Simulation project
PHASE 0
Launch readiness
Nov–Dec 2026
Internal teams
Security, UAT, hardening
Exit gate
Go / no-go on 4 Dec
PHASE 1
Pilot
Jan–Mar 2027
10 merchants
Enterprise e-commerce
Exit gate
Activation ≥ 60%, on-time ≥ 90%, zero card data incidents
PHASE 2
Wave 1
Mar–May 2027
3,000 merchants
~62% of dispute volume
Exit gate
Portal share ≥ 35%, missed-deadline loss ≤ 5%
PHASE 3
Wave 2
Jun–Sep 2027
5,400 merchants
~88% of dispute volume
Exit gate
Portal share ≥ 50%, handling time ≤ 30 min
PHASE 4
General availability
Oct–Dec 2027
24,900 merchants
~93% of dispute volume
Exit gate
Email intake retired for portal-enabled merchants
Every expansion checks five gates
Adoption
Activation and portal share on target
Outcomes
On-time response trending to target
Security
No open critical or high findings
Operations
Capacity and support model ready
Data
KPI tracking and reconciliation live
Notes: Merchant counts are cumulative. Waves expand on evidence, not on the calendar.

## Slide 11
TOP RISKS
Five open risks need executive visibility
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
R-04
Low merchant adoption of the portal
Pilot with 10 high-volume merchants; in-portal onboarding; adoption tracking; email retired wave by wave
Owner Product Owner
16 · High
R-02
Card numbers in evidence expand PCI DSS scope
Automated redaction on upload (CR-03); quarantine; InfoSec validation before UAT sign-off
Owner Tech Lead
15 · High
R-03
Status sync lag causes missed deadlines
Feed-freshness alerts; 'last synced' timestamp; reminders at 5 and 2 days
Owner Tech Lead
15 · High
R-01
Card network rule changes before go-live
Configurable reason codes and response windows (CR-02)
Owner Product Owner
12 · Medium
R-05
Legacy settlement data quality undermines reports
Data quality rules; exception report; reconciliation before sign-off
Owner Data Engineering Lead
12 · Medium
Scores are likelihood × impact on a 1–5 scale (RAID Log).
Notes: R-04 is the swing factor for the business case. R-02 and R-03 are control risks with owners and mitigations already in the backlog.

## Slide 12
CHANGE CONTROL
Change control is working, but schedule contingency is nearly used up
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
9 of 10
Contingency days used by approved changes
4
Change requests pending, of 9 logged (3 approved, 1 rejected, 1 deferred)
60%
Approval rate: 3 approved of 5 decided
5 Jan 2027
Forecast go-live if all pending changes are approved as requested (baseline 11 Dec 2026)
Recommended decisions
CR-01 · Fraud case scope
Keep full fraud case management out of MVP; add a read-only linked case reference (Option C), with a Phase 2 commitment.
CR-05 · Outcome definitions
Report Won, Partially won and Lost separately (Option C) and govern one definition before KPI reporting starts.
CR-06 · UAT approach
Run UAT in parallel with the delayed pen test only where Compliance and InfoSec controls allow; protect the go-live gate.
Protect the MVP baseline: treat any late scope as an explicit trade-off against the 11 December 2026 go-live.
Notes: Only one contingency day is left. Any further scope has to be traded against the date.

## Slide 13
LAUNCH READINESS
Two vendor dependencies are already committed later than needed
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
0 of 19
Launch readiness items done so far; 14 are critical for the go-live gate
D-01 · Processor dispute API production access
Provider: Payment processor
At risk
Needed 16 Oct · committed 23 Oct
D-03 · Penetration test before UAT
Provider: InfoSec
At risk
Needed 30 Oct · committed 13 Nov
Go-live requires
✓ UAT sign-off
✓ Critical and high pen test findings fixed
✓ InfoSec redaction validation
✓ Load test passed at 3× peak
✓ Accessibility sign-off
✓ Dispute Ops and servicing trained
✓ Rollback plan tested
✓ Hypercare rota and KPI tracking ready
Hypercare 11 Dec 2026 – 22 Jan 2027. Exit is based on evidence, not the date: 10 consecutive business days with no open Sev 1 or Sev 2, sync latency p95 ≤ 5 min, zero card data incidents, runbooks accepted, and support running without the delivery team.
Notes: Neither dependency is under the delivery team’s control. Leadership help is requested on both in the recommendation slide.

## Slide 14
TIMELINE
From build to general availability
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
20 Jul 2026
Build starts
9 Nov 2026
Hardening and UAT
4 Dec 2026
Go / no-go
11 Dec 2026
Go-live
22 Jan 2027
Hypercare exit
11 Mar 2027
Pilot exit review, Wave 1 go / no-go
24 Sep 2027
Wave 2 complete
17 Dec 2027
General availability complete
Build
20 Jul – 6 Nov 2026
Hardening and UAT
9 Nov – 4 Dec 2026
Hypercare
11 Dec 2026 – 22 Jan 2027
Pilot
11 Jan – 5 Mar 2027
Waves 1 and 2
15 Mar – 24 Sep 2027
General availability
4 Oct – 17 Dec 2027
Dark cards: phases in progress or next. The pilot runs inside hypercare; its exit review on 11 March decides Wave 1.
Notes: Corrected from earlier drafts: the pilot ends 5 March, and the exit review that decides Wave 1 is 11 March.

## Slide 15
ROADMAP
MVP is the foundation; the destination is dispute prevention
30 initiatives on Product Roadmap v1.1 · horizons measured from 11 September 2026
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
NOW
6 initiatives
• MVP build, hardening, go-live and hypercare
• Outcome definitions (CR-05)
• Analytics tracking plan (I-06)
• Fraud case reference (pending CR-01)
NEXT
15 initiatives
• Pilot, Waves 1 and 2, retire email intake
• Evidence guidance, templates, reason code admin
• Spanish portal and fraud case management (Phase 2)
New
Dispute ratio health alerts · RM-28
New
Pre-dispute alerts and early refunds · RM-25
New
AI evidence copilot pilot · RM-26
LATER
9 initiatives
• General availability, auto-accept rules
• Marketplace model, dispute API, premium service
New
Friendly fraud evidence automation · RM-27
New
Root-cause insights · RM-29
New
AI agent purchase readiness · RM-30
New = proposed from the Discovery & Decision Log. Each needs discovery, compliance review and a business case; the AI copilot also needs a model risk review (17 Jun 2027).
Notes: Horizons match wireframes S09 to S13 and the roadmap workbook. The point is processing today, optimization next, prevention later.

## Slide 16
THE ASK
Five decisions leadership needs to make
Section 3 of 3 · Risks, change control and decisions
Merchant Payment Operations & Dispute Hub · Simulation project
Decision
Approver
Needed by
CR-05
Approve dispute outcome and win-rate definitions
Business Sponsor
18 Sep 2026
CR-01
Decide fraud case management scope for the MVP
Steering Committee
24 Sep 2026
CR-06
Approve running UAT in parallel with the delayed pen test
Steering Committee
25 Sep 2026
I-06
Approve the analytics tracking plan, needed to measure pilot activation
Data Governance Lead
1 Oct 2026
LR-17
Agree treatment of released Ops capacity: cashable or redeployed
Finance Lead
30 Oct 2026
Four decisions fall due by 1 October; the capacity decision (LR-17) is due 30 October.
Notes: Dates match the Change Log, RAID Log and Engagement Plan governance calendar.

## Slide 17
RECOMMENDATION
Endorse the base case, clear four decisions by 1 October, and the capacity decision by 30 October
1
Endorse the base-case investment ($149k NPV, 26% ROI, 2.3-year payback), noting the conservative case is negative
2
Approve the pilot-led rollout, with its KPI exit gates as go / no-go criteria for each wave
3
Resolve CR-05, CR-01, CR-06 and I-06 by 1 October, and LR-17 by 30 October
4
Help unblock the two at-risk dependencies: processor production access (D-01) and the InfoSec penetration test (D-03)
Next governance touchpoint: Steering Committee, 24 September 2026
Supporting detail: PRD v1.2 · Product Roadmap v1.1 · KPI Definitions v1.1 · Discovery & Decision Log v2.0 · RAID Log · Change Log · RTM · Business Case & GTM · Engagement Plan · Post-Launch Plan · Wireframes v1.1
Simulation project: a Product Owner portfolio exercise. Not an actual client system.
Notes: Close on the decisions, not a thank-you. Offer the supporting documents if leadership wants detail.